## Master list
Version History: v1.0 - 01 Feb 2016 - first version (pilot phase) v2.0 - 10 Jan 2017 - addition of various rows and numbering system (pilot phase) v3.0 - 16 Nov 2017 - minor corrections released with SOP (live phase) v4.0 - 01 Aug 2018 - temporary halt included within section 26
Division of Responsibilities
Date and version of document:
Study title:
Study reference:
Sponsor:
CI:
CTU:
| Activities (listed in study conduct order) |  | Responsible Parties
Number | Top level | Subdivision | Sponsor | CI | CTU
1 | Funding
1.1 |  | Identify and invite co-applicants
1.2 |  | Secure funding
1.3 |  | Budget management
1.4 |  | Report to funder
2 | Trial design
2.1 |  | Develop research idea including scientific rationale, clinical relevance, clinical feasibility
2.2 |  | Obtain statistical advice, including Sample size calculation
2.3 |  | Obtain peer review
3 | Protocol
3.1 |  | Obtain EudraCT number and relevant registrations
3.2 |  | Protocol preparation (including internal departmental review)
3.3 |  | Protocol review
3.4 |  | Protocol sign-off
4 | Risk Assessment
4.1 |  | Develop, review and update risk assessment
4.2 |  | Develop, review and update risk related plans e.g. monitoring plan
5 | Sponsorship and Insurance
5.1 |  | Confirm Sponsorship
5.2 |  | Arrange insurance and / or where appropriate indemnity
6 | Trial Master File
6.1 |  | Prepare and maintain Trial Master File (TMF)
7 | Service and Supply
7.1 |  | Identify appropriate providers in line with applicable policy
7.2 |  | Source study product
7.3 |  | Source other suppliers such as CRO, lab, pharmacy, courier
7.4 |  | Provide trial equipment supplies
7.5 |  | Obtain / provide randomisation service
7.6 |  | Identify appropriate contracts
7.7 |  | Negotiate appropriate contracts
7.8 |  | Sign off appropriate contracts
8 | Site Selection and Management
8.1 |  | Identify, select and recruit sites / centre / hubs / investigators
8.2 |  | Negotiate contract with sites
8.3 |  | Sign off of contracts with sites
8.4 |  | Provide information to sites (including newsletters)
8.5 |  | Conduct site training and setup
8.6 |  | Put and keep in place training / arrangements to allow investigators to conduct the trial according to the Protocol, GCP and applicable regulations
8.7 |  | Provide Investigator Site File (ISF)
8.8 |  | Distribute trial documents to sites
8.9 |  | Activate authorised sites
8.1 |  | Oversee performance of sites
8.11 |  | Administer changes at site (including PI change)
8.12 |  | Close out sites
9 | Site Conduct
9.1 |  | Obtain authorisation from local regulatory bodies (e.g. host organisation)
9.2 |  | Ensure adequate facilities, resources and support are available to conduct the study
9.3 |  | Maintain ISF
9.4 |  | Ensure the rights of individual participants are protected and that they receive appropriate medical care whilst participating in the trial
9.5 |  | Ensure that no participant is recruited at site until the participating site has been activated
9.6 |  | Ensure that the appropriate consent has been provided by the participants
9.7 |  | Ensure the appropriate delegation logs are maintained and kept up to date
9.8 |  | Ensure overview of operational day-to-day business
9.9 |  | Ensure that the study is conducted locally according to GCP, all relevant legislation and the Protocol
9.1 |  | Submit all study data and material required for the study, in accordance with the Protocol and any study specific manuals.
9.11 |  | Report SAEs, protocol deviations and all serious breaches of study conduct and / or GCP as required
9.12 |  | Ensure that study IMP supplies for specific use in the study are used in strict accordance with the Protocol and are not used for any other purpose.
9.13 |  | Maintain study product storage and accountability
9.14 |  | Ensure that all Clinical Data and documentation are available for the purposes of monitoring, inspection or audit
10 | Ethics Approval
10.1 |  | Prepare submission bundle
10.2 |  | Review submission bundle
10.3 |  | Sign off submission bundle
10.4 |  | Submit submission bundle
10.5 |  | Obtain positive opinion from appropriate research ethics committee
10.6 |  | Submit and distribute annual progress reports
11 | Competent Authority Approval
11.1 |  | Prepare submission bundle
11.2 |  | Review submission bundle
11.3 |  | Sign off submission bundle
11.4 |  | Submit submission bundle
11.5 |  | Obtain competent authority authorisation
11.6 |  | Submit and distribute annual safety reports (e.g. DSUR)
12 | Other Approvals
12.1 |  | Obtain relevant national host organisation approval e.g. HRA
12.2 |  | Obtain local agreement for trial conduct
13 | Trial Management
13.1 |  | Develop project plan/ overview of timelines
13.2 |  | Ensure adherence to and adoption of University of Oxford Core SOPs
13.3 |  | Ensure that the CTU/ coordinating centre staff are appropriately qualified / trained / educated to conduct the study and where applicable honorary employment contracts are in place
13.4 |  | Coordinate Investigator meetings
13.5 |  | Ensure third parties compliance to appropriate regulations and other requirements
13.6 |  | Ensure that no participant is recruited to the trial until satisfied that all relevant permissions and approvals have been obtained.
13.7 |  | Ensure that no participant is recruited to the trial or study activated until satisfied that all relevant systems and resources are in place.
13.8 |  | Ensure the participants confidentiality is maintained in accordance with relevant legislation including the Data Protection Act
14 | CRF/eCRF design
14.1 |  | Design and prepare CRF
14.2 |  | Review and validation CRF
14.3 |  | Generate CRF guidelines
14.4 |  | Sign off CRF
15 | Database design
15.1 |  | Design and build database
15.2 |  | Design and build participant registration or randomisation database
15.3 |  | Conduct system testing and validation
15.4 |  | Conduct user acceptance testing
15.5 |  | Conduct database user training
16 | Data Management
16.1 |  | Oversee or prepare data management plan
16.2 |  | Oversee or prepare other detailed manual as required e.g. imaging
16.3 |  | Data coding
16.4 |  | Data entry
16.5 |  | Data checks
16.6 |  | Track CRFs
16.7 |  | Ensure data timeliness and quality
16.8 |  | Query management
16.9 |  | Data transfer approval
16.1 |  | Data transfer
16.11 |  | Database reconciliation
16.12 |  | Database lock
17 | Code breaking
17.1 |  | Define emergency code breaking procedures (if applicable)
17.2 |  | Provide emergency code breaking (if applicable)
18 | IMP management
18.1 |  | Source IMP in line with relevant procurement rules
18.2 |  | Ensure retention of IMP documentation (e.g. certificate of analysis, IMP packaging sample etc.)
18.3 |  | Ensure labelling and QP release
18.4 |  | Ensure that all sites are at all times in possession of the current information on the IMP
18.5 |  | Ensure that sufficient IMP is available to participants free of charge
18.6 |  | Distribute study product to sites
18.7 |  | Maintain study product accountability
18.8 |  | Ensure appropriate destruction of IMP and maintain detailed records
19 | Device management
19.1 |  | Ensure that investigational medical devices are not used for any purpose other than the conduct of the study, unless specific permission is given
19.2 |  | Ensure that investigational medical devices are stored in appropriate, secure conditions and returned as instructed
19.3 |  | Ensure detailed records are maintained regarding movement from delivery to return / destruction
20 | Sampling handling
20.1 |  | Oversees, prepare and maintain lab / sample handling manual
20.2 |  | Prepare and maintain appropriate SOP for sample handling
20.3 |  | Ensure sample receipt and tracking
20.4 |  | Administer laboratory supplies
20.5 |  | Transfer of appropriate analysis results to study database
20.6 |  | Organise appropriate retention or disposal of samples on completion of study
21 | Monitoring
21.1 |  | Conduct and document monitoring according to monitoring plan
22 | Audit and Inspection
22.1 |  | Plan and conduct audits appropriate to trial
22.2 |  | Facilitate audits and inspections
23 | Safety Reporting
23.1 |  | Define reportable events in protocol
23.2 |  | Ensure RSI definition, provision and revision
23.3 |  | Ensure access has been gained for eSUSAR, Eudravigilance (or equivalent) and EudraCT results database (or equivalent)
23.4 |  | Arrange appropriate systems and data collection documentation related to safety
23.5 |  | Keep records of safety events
23.6 |  | Assess safety events
23.7 |  | Review SAE
23.8 |  | Issue of queries for SAE
23.9 |  | Ensure appropriate follow-up of SAE
23.1 |  | Report SUSAR/unexpected and related SAE to CA, ethics, Sponsor, host organisation as required
23.11 |  | Report safety concerns to investigators including SUSARs
24 | Serious Breach
24.1 |  | Identify potential serious breach
24.2 |  | Report potential serious breaches to Sponsor
24.3 |  | Classify incidents as a serious breach
24.4 |  | Report serious breach to CA
24.5 |  | Provide follow-up information on a serious breach
25 | Complaint
25.1 |  | Receipt of complaint
25.2 |  | Investigation of complaint
25.3 |  | Communication with Insurers
26 | Amendments including Urgent Safety Measures and Temporary Halts
26.1 |  | Identify, communicate and implement urgent safety measures
26.2 |  | Report any stoppage in study activities of any form which are anticipated or proves to be more than one month and may result in the need to implement a formal temporary halt to Sponsor
26.3 |  | Prepare amendment submission bundle
26.4 |  | Review amendment submission bundle
26.5 |  | Sign off amendment submission bundle
26.6 |  | Submit amendment submission bundle
26.7 |  | Obtain approval/positive opinion from appropriate bodies
26.8 |  | Provide appropriate details to all participating R&Ds / host organisations
27 | Committee Management
27.1 |  | Identify and invite members for committees (in line with funder regulations)
27.2 |  | Coordinate Trial / Project Management Group
27.3 |  | Report to Trial / Project Management Group
27.4 |  | Coordinate Trial Steering Committee
27.5 |  | Report to Trial Steering Committee
27.6 |  | Coordinate Data Monitoring Committee
27.7 |  | Report to Data Monitoring Committee
28 | Statistical analysis
28.1 |  | Develop statistical analysis plan
28.2 |  | Review and agree statistical analysis plan
28.3 |  | Conduct statistical analysis (interim and final)
28.4 |  | Prepare trial report
28.5 |  | Review trial report
28.6 |  | Sign off trial report
29 | Publication
29.1 |  | Prepare publication draft
29.2 |  | Review publication
29.3 |  | Submit publication
29.4 |  | Disseminate into applicable databases including copy to Sponsor
30 | Close out
30.1 |  | End of trial or early termination communication (including end of study report) to CA, ethics, Sponsor, host organisation as applicable
30.2 |  | Reconcile trial finances
30.3 |  | Terminate service agreements
31 | Archiving
31.1 |  | Ensure that all study records held at site are archived appropriately when notified to do so and retained as required
31.2 |  | All relevant and appropriate study documentation collated in preparation for archiving
31.3 |  | Archived by Named Archivist

## Suggested additional items
Activities (listed in study conduct order)
Top level | Subdivision | Additional items for consideration | Comments
Funding
Scientific reports vs financial reporting
Service and Supply
Negotiations with suppliers / services that fall outside normal requirements
Calibration certificates
|  | Obtain contract with third parties | In this section service is referring to providing a task in return for payment with no onward expectations of recognition in publication or IP
Site Selection and Management
CV and GCP certificates
IMP Management
| IMP storage (e.g temperature logs) | Disposal of spoilt IMP
Disposal of unused IMP
Retention of sample packaged IMP
IMPD production maintenance
Data Management
| CRF review and validation |  | It maybe necessary to separate these two points out
| Query Management | Creation of data query sheets
Query distribution
Monitoring
| Conduct and document monitoring according to monitoring plan | Identification of data and information for monitoring
Identification of site for site monitoring
Central monitoring
Monitoring sites including SDV
Site initiation visits
Monitoring activities
Production of monitoring reports
Review and sign off of monitoring reports
Respond to monitoring reports
Close out visits
Statistical analysis
| Statistical analysis (interim and final) | Conducting codebreaking for data analysis
Close out and Archiving
| Archiving | Archiving location
Retrieval procedure
Retention period
Destruction